## Sheet1
Woche	Datum	Milestones					Woche	Datum	Milestones
1	28. Jul. 2019	Heuristics Parameter / Estimation	Parameter Values, / Text on Methods and Sources		Done		1	28. Jul. 2019	Heuristics Parameter / Estimation
2	4. Aug. 2019	Heuristics Story, / Experiment Design / And evaluation			Done		2	4. Aug. 2019	Heuristics Story, / Experiment Design / And evaluation
3	11. Aug. 2019	Heuristics Story, / Experiment Design / and evaluation			Done		3	11. Aug. 2019	Heuristics Story, / Experiment Design / and evaluation
4	18. Aug. 2019	Heuristics writing / Discussion			Done		4	18. Aug. 2019	Heuristics writing / Discussion
5	25. Aug. 2019	Conclusion and / Intro to savings		Parallel: / Finalization of / Heuristics Chapter, / Revision for / Approximation Paper, / Write Introduction to / MayaSim Paper			5	25. Aug. 2019	Conclusion and / Intro to savings
6	1. Sep. 2019	Shot part on Yukis / Thesis: Adapt fig. 1 and fig 2.					6	1. Sep. 2019	Shot part on Yukis / Thesis: Adapt fig. 1 and fig 2.
7	8. Sep. 2019	Rewrite Introduction / To Approximation paper	Rather start thinking about all / The Introductions that I need / For the entire thesis?				7	4. Sep. 2019	Update Approximation Paper
8	15. Sep. 2019	Rewrite Conclusion / To Approximation paper	I think, the conclusion is fine.. / Maybe add some parts that fit / Into the general structure of the Thesis				7	5. Sep. 2019	Update Mayasim Paper
9	22. Sep. 2019	Rewrite Introduction the / Mayasim Paper, Rewrite / Conclusion to Maysim Paper / and Motivate further Work in / This Thesis					7	6. Sep. 2019	Content and General Structure / Of Introduction
10	29. Sep. 2019	Final Interviews, Evaluation / And Writing of text					8	15. Sep. 2019	General Introduction / Written
11	6. Oct. 2019	Content and General Structure / Of Introduction					9	22. Sep. 2019	Final Conclusion	Send out for Comments after Week 9?
12	13. Oct. 2019	General Introduction / Written					10	29. Sep. 2019	Final Interviews, Evaluation / And Writing of text
13	20. Oct. 2019	Final Conclusion / Written
14	27. Oct. 2019	Send out for Comments, / Do Leftover Stuff
15	3. Nov. 2019	Working on Comments, / Final Editing					14	27. Oct. 2019	Send out for Comments, / Do Leftover Stuff
							15	3. Nov. 2019	Working on Comments, / Final Editing

	Sections	Subtasks:

	Mayasim	Coordinate with Maurits	Write Conclusion	Hand in	Reedit Intro and / Conclusion
	Introduction	Collection of Content / And Structure	Writing
	Heuristics	Parameter Estimation	Experiments / (Design and Implementation)	Evaluation	Story	Intro/Überleitung
	Savings	Story	Intro/Überleitung	Figure(s) anpassen
	Approximation	Intro/ueberleitung	Conclusion überarbeiten
	Interviews	Interview mit Pavel und Jobst	Auswerten	Interpretation/Conclusion
	Conclusion	Collect Points	Write
	Methods?	Collect what might / Be necessary
	Other Stuff	Comments	Editing and Formal / Requirements	Handing In and administrational / Stuff that comes with that