## Sheet1
Woche	Datum	Milestones
1	28. Jul. 2019	Heuristics Parameter / Estimation	Parameter Values, / Text on Methods and Sources
2	4. Aug. 2019	Heuristics Story, / Experiment Design / And evaluation
3	11. Aug. 2019	Heuristics Story, / Experiment Design / and evaluation
4	18. Aug. 2019	Heuristics writing / Discussion
5	25. Aug. 2019	Conclusion and / Intro to savings
6	1. Sep. 2019	Shot part on Yukis / Thesis: Adapt fig. 1 and fig 2.
7	8. Sep. 2019	Rewrite Introduction / To Approximation paper
8	15. Sep. 2019	Rewrite Conclusion / To Approximation paper
9	22. Sep. 2019	Rewrite Introduction the / Mayasim Paper, Rewrite / Conclusion to Maysim Paper / and Motivate further Work in / This Thesis
10	29. Sep. 2019	Final Interviews, Evaluation / And Writing of text
11	6. Oct. 2019	Content and General Structure / Of Introduction
12	13. Oct. 2019	General Introduction Written
13	20. Oct. 2019	Final Conclusion Written
14	27. Oct. 2019	Send out for Comments, / Do Leftover Stuff
15	3. Nov. 2019	Working on Comments, / Final Editing

	Sections	Subtasks:

	Mayasim	Coordinate with Maurits	Write Conclusion	Hand in	Reedit Intro and / Conclusion
	Introduction	Collection of Content / And Structure	Writing
	Heuristics	Parameter Estimation	Experiments / (Design and Implementation)	Evaluation	Story	Intro/Überleitung
	Savings	Story	Intro/Überleitung	Figure(s) anpassen
	Approximation	Intro/ueberleitung	Conclusion überarbeiten
	Interviews	Interview mit Pavel und Jobst	Auswerten	Interpretation/Conclusion
	Conclusion	Collect Points	Write
	Methods?	Collect what might / Be necessary
	Other Stuff	Comments	Editing and Formal / Requirements	Handing In and administrational / Stuff that comes with that